## Activity monitoring
Activity monitoring
Youth and Development NGO of Girl Scouts of Senegal (JED / EEDS) |  |  | TITLE: ECLAT (be like the others and forever) Energy for schools
Activity report |  | Year 2020
|  | T1 |  |  | T2 |  |  | T3 |  |  | T4
A1: The learning conditions for students in target schools are improved |  | Activities carried out during the quarter | Difficulties and solutions sought | Comments and suggestions | Activities carried out during the quarter | Difficulties and solutions sought | Comments and suggestions | Activities carried out during the quarter | Difficulties and solutions sought | Comments and suggestions | Activities carried out during the quarter | Difficulties and solutions sought | Comments and suggestions
Activity 1 | Identify schools and children to benefit from project support |  |  |  | This TRIM2 is upset by the appearance of the Coronavirus. The government has decided to close all schools as part of the response to COVID19. |  |  | This TRIM coincided with the gradual lifting of measures related to the response against the Coronavirus. However, only students in exam class have resumed classes
Sub activity 1.1.1 | Set up an educational committee in each department made up of project staff, education inspectors, school directors and parents to support the entire project process | 1 educational committee is set up in the department of Tivaouane. In Thiès, collaboration with the IEF is underway
Sub activity 1.1.2 | Organize a series of prospecting visits to the targeted schools | 10 schools were visited by the project | The schools are very distant (educational breakdown). |  | On resumption in the 2nd week of June, 4 schools were visited as part of the improvements |  |  | 8 schools were visited during this quarter by the project team. In each school, a meeting took place with the actors
Sub activity 1.1.3 | Hold a meeting in each department to validate the choices of beneficiaries with all the stakeholders | 2 meetings take place in each department (1 on sharing the project and 1 after signing the agreement with PADEM)
Activity 1 .2 | Equip schools and children with solar energy
Sub activity 1 .2.1 | Equip students with solar street lights to facilitate learning | In the surveys, the files provided information on the number of students who did not have access to eletcrity at home. |  | The technicians are thinking about the adequate kit that will benefit the family
Sub activity 1 .2.2 | Equip targeted schools with solar electricity | 2 schools have been installed (Electricité Sénélec) and 1 other has been completed with its sizing for solar. 1 school in Mboro is supported to restore electricity after strong winds |  | These 2 schools out of 3 have chosen Sénélec electricity, which is assessed as more accessible (Post next to it) | On resumption in the 2nd week of June, 1 school was installed in solar |  | During confinement, Senelec connected electricity for the Darou Marnane school | 3 schools have benefited from installation for access to electricity. The 2 have already had the connection to electricity
Sub activity 1 .2.3 | Train young people in the maintenance of solar equipment through information and demonstration times
Activity 1.3 | Implement a school development program (Ringtone; Reforestation; School gardens) in collaboration with school governments | 1 school in Tivaouane benefited from reforestation after installation for the current
R2: The academic performance and retention of students in school are effective
Activity 2.1 | Sensitize beneficiary communities to retaining students and promoting childhood |  |  |  | This TRIM2 is upset by the appearance of the Coronavirus. The government has decided to close all schools as part of the response to COVID19. |  |  | The measures related to the response against the coronavirus did not facilitate the holding of these actions
Sub activity 2.1.1 | Organize discussion sessions around the school (maintenance of children; civil status; management of the framework; student performance, etc.) with the groups of school directors, management committees and parents of children | 7 discussion sessions were held on access to school, maintenance, civil status |  | Attention was paid to the school by the affected actors
Sub activity 2.1.2 | Hold awareness campaigns (Social mobilization) on keeping children in school in collaboration with children, parents, teachers
Sub activity 2.1.3 | Commemorate the periodic days for the promotion of children in collaboration with school governments
Activity 2.2 | Train student school governments in the upkeep and maintenance of facilities and management of the school environment
Sub activity 2.2.1 | Support the installation, revitalization and operation of school governments | 3 schools have had their school government installed. Student participation was ensured throughout the process |  | An action highly appreciated by the students and by the educational body
Sub activity 2.2.2 | Organize training and information sessions for the benefit of students on the management of the school environment and the upkeep and maintenance of facilities
Activity 2.3 | Train young community assistants for the pedagogical reinforcement of weak students
Sub activity 2.3.1 | Hold training workshops for young community assistants on pedagogical coaching techniques
Sub activity 2.3.2 | Roll out an educational reinforcement program for weak students
Activity 2.4 | Support the development, implementation and monitoring of action plans for management committees in schools
Activity 2.5 | Roll out a program of information and mobilization of local authorities for the sustainability of facilities and the promotion of the complete electrification of schools. | The Sénélec manager of each zone was met with a view to facilitating access to electricity for schools |  | These managers made it easier for the schools and the project |  |  |  | The project took advantage of the territorial conference convened by the Prefect to invite the decision makers to take this question as a priority.
R3: Good practices are capitalized and popularized with decision-makers and communities
Activity 3.1 | Organize regular meetings to monitor the project and share successes with the educational committee and partners |  |  |  | This TRIM2 is upset by the appearance of the Coronavirus. The government has decided to close all schools as part of the response to COVID19.
Sub activity 3.1.1 | Hold quarterly meetings of the educational committee to monitor project actions | 2 meetings took place including 1 in Thiès with the IEF and 1 others in Tivaouane with the educational committee |  | The educational committee facilitated the sharing of information among other school stakeholders
Sub activity 3.1.2 | Organize annual meetings to share capitalization successes with all stakeholders
Activity 3.2 | Organize information campaigns for the general public
Sub activity 3.2.1 | Report 10 success stories during the project | [6 empty] | 1 film on the project was produced during this quarter. He highlighted some achievements
Sub activity 3.2.2 | Broadcast 48 radio and / or infomercial programs with local and national media | The heads of community radio stations in Mboro, Ngaye were met with a view to a convention. For that of Mboro, a grid is proposed
Activity 3.3 | Participate in local and national meetings on the elementary education sector | During the meeting with the LARTES laboratory, a set of tools on school repetitions were made available to the project | [5 empty] | The territorial conference convened by the Prefect was an opportunity to talk about the project and its proposals
Overall project report
Did you face any difficulties during the realization of the project this quarter? If yes, explain the difficulties and possible solutions |  | There was a little delay in the availability of funds. However, the project thus opted to carry out prospecting visits and meetings with the authorities in advance. |  |  | The closure of schools during this pandemic has forced the plan to cancel a large part of the activities. |  |  | The measures related to the response against the coronavirus have meant that some activities with students or parents have not been held
Have there been any adaptations / modifications to the logical framework or to the strategy during the progress of the project carried out? |  | NO |  |  | YES. After the relaxation of the measures, it was decided to go to the facilities and wait for the return of the students to TRIM3 for actions requiring the participation of the latter. |  |  | Yes. During this quarter he was put in front of the installations. During the upcoming trimester, the hope to start with the children, parents, etc. is there with the reopening of schools
Is there a big difference between the budget planned and the expenses made during this quarter? If so, explain why. |  | NO |  |  | YES
What are the prospects in terms of sustainability of the project? |  | In each school, a significant mobilization of the educational body, parents and local stakeholders is noted. | [5 empty] | It was noted an interesting engagement of the actors of the school of Yendaan in Pambal. Parents helped set up the school. Many initiatives are in sight to improve the school environment
Do you have any other important information to include? |  | Concerning the school management committees, the financing of their action plans is temporarily suspended by the State with a view to reorganization |  |  | During confinement, Sénélec connected electricity for Darou Marnane primary school in Mboro

## Monitoring indicators
Monitoring of indicators
TITLE: ECLAT (being like the others and forever) "Energy for schools"
Overall objective: Contribute to better access for children in the Thiès Region to quality education
Specific objective: Improve school performance and student retention through the provision of quality services
Result 1: The learning conditions of students in target schools are improved
Year 1 (2020)
Indicator | Planned (global project) | TR1 | Comments | TR2 | Comments | TR3 | Comments | TR4 | Comments
Many schools have access to electricity | 60 | 3 | 1 school restored and 2 installed | 2 | 1 school connected and 1 in solar installed | 3
Many students in vulnerable situations have access to solar energy | 10000
Number of schools fitted out for a better living environment | 30 | 1
Solar installations are functional and maintained | 60
Number of students trained and involved in the maintenance of facilities
Educational committee installed and functional | 2 | 1 | Department of Tivaouane. In Thiès the authority is involved
Result 2 - The academic performance and retention of students in school are effective
Indicator |  | TR1 | Comments | TR2 | Comments | TR3 | Comments | TR4 | Comments
The success rate of students in beneficiary schools is improved | 25%
Number of junior assistants trained for repetition of weak students | 120
Teaching reinforcement program for weak students | 1
Number of school governments installed and supported | 60 | 3 | A dynamic and participatory process
Number of training sessions held at students' locations | 60
Number of days dedicated to children celebrated with school governments | 8
Number of discussion sessions held on student maintenance, civil status, management of facilities and amenities | 60 | 7
Number of mobilization sessions held on student maintenance, civil status, management of facilities and amenities | 60
Number of people made aware during discussions and mobilizations | 5000 | 210 | Educational body, Parents, Local actors
School management committees are functional with an action plan developed and implemented | 60
Number of municipal councils that have taken decisions in favor of electrification and the development of schools
Result 3 - Good practices are capitalized and disseminated to decision-makers and communities
Indicator |  | TR1 | Comments | TR2 | Comments | TR3 | Comments | TR4 | Comments
A capitalization and monitoring framework is available | 1 | 1
Success stories are recorded, tracked and documented | 10 |  |  |  |  | 1 | 1 film was made during this quarter
Number of popularizations of successful cases in the branches through the region's media | 48
Number of meetings between all stakeholders | 4 | 3
Database reporting the services from which children benefit is completed and available | 1 | 1 | Being created